## Instructions
CostCubes — Cost Intelligence & Business Performance
FN-PRJ-001 · Projects, Engineering & Capex Register · version 1 · Projects, Engineering & Maintenance
Capex, engineering, maintenance and improvement projects with budget, forecast at completion, schedule, stage and benefits (₹ lakh).
FICTIONAL DEMONSTRATION DATA — Apex Plastics & Household Products Pvt. Ltd. is not a real company. All names, figures and results are illustrative. Sample limited to the first 300 rows.
1. Enter one row per project in the "Data" sheet, starting on row 11. Do not rename sheets or column headers, and do not delete the hidden "_coin" sheet.
2. Columns marked "Mandatory" on row 9 must be completed on every row. "Project_ID" must be unique within the file.
3. Dates: enter real Excel dates (for example 15-Oct-2026). Month columns accept a date or text such as Oct-2026 or 2026-10.
4. Percentages: enter the number of percent (12.5 means 12.5%). Amount columns are in the currency and unit named in the column header (for example ₹ or ₹ lakh).
5. Use the same product, material, customer and supplier codes across all CostCubes templates. Product codes are checked against your Product Master (FN-MST-001) when it is uploaded.
6. Optional sheets: "KPI_Summary" for the targets and actuals your function reports, and "Actions" for open projects, issues and corrective actions with owners and target dates.
7. Calculated columns (for example Scrap_% or Variance) are re-checked by CostCubes; differences are reported as warnings with the row number. Rows are never silently dropped.
8. Save as .xlsx (Excel Workbook). Macro-enabled (.xlsm) and legacy .xls files are not accepted. Upload in your CostCubes portal → Upload centre.
Columns
Project_ID — unique identifier · mandatory
Project_Name — text · mandatory
Type — text · optional
Sponsor — text · optional
Project_Manager — text · mandatory
Business_Case — text · optional
Budget_INR_Lakh — amount · mandatory
Actual_Spend_INR_Lakh — amount · optional
Forecast_At_Completion — amount · optional
Start_Date — date · mandatory
Target_Date — date · mandatory
Actual_Completion_Date — date · optional
Stage — choice · mandatory · suggested: Proposed, Approved, Execution, Commissioning, Closed, On hold
Completion_% — percentage (number of %) · optional
Schedule_Variance_Days — whole number · optional
Benefit_Target_INR_Lakh — amount · optional
Benefit_Realised_INR_Lakh — amount · optional
Risk_Level — choice · optional · allowed: Low, Medium, High
Next_Milestone — text · optional

## Data
CostCubes functional register
Template code |  | FN-PRJ-001
Template name |  | Projects, Engineering & Capex Register
Version |  | 1
Client code |  | DEMO-PL-001
Currency |  | INR
Reporting period |  | As at 30-Sep-2026
Units |  | As labelled in column headers
Mandatory | Mandatory | Optional | Optional | Mandatory | Optional | Mandatory | Optional | Optional | Mandatory | Mandatory | Optional | Mandatory | Optional | Optional | Optional | Optional | Optional | Optional
Project_ID | Project_Name | Type | Sponsor | Project_Manager | Business_Case | Budget_INR_Lakh | Actual_Spend_INR_Lakh | Forecast_At_Completion | Start_Date | Target_Date | Actual_Completion_Date | Stage | Completion_% | Schedule_Variance_Days | Benefit_Target_INR_Lakh | Benefit_Realised_INR_Lakh | Risk_Level | Next_Milestone
PRJ-001 | Mould 42 cycle-time reduction | Productivity | R. Shah | V. Rao | Reduce cycle from 38 sec to 32 sec | 42 | 25 | 45 | 2026-07-01 | 2026-11-30 |  | Execution | 60 | 5 | 90 | 18 | Medium | Trial run on 3 cavities
PRJ-002 | Warehouse barcode rollout | Digital | N. Shah | D. Joshi | Improve stock accuracy and traceability | 18 | 8 | 20 | 2026-08-15 | 2026-12-15 |  | Execution | 35 | 0 | 35 | 3 | High | Pilot at FG staging
PRJ-003 | Recycled resin validation | Sustainability | A. Mehta | A. Kulkarni | Validate recycled content on 4 products | 12 | 2 | 12 | 2026-10-01 | 2027-02-28 |  | Proposed | 5 | 0 | 28 | 0 | High | Lab trial and customer sample
PRJ-004 | IM-07 hot-runner refurbishment | Maintenance | R. Shah | V. Rao | Reduce downtime and warping on IM-07 | 24 | 21 | 29 | 2026-05-01 | 2026-08-31 |  | Commissioning | 85 | 45 | 40 | 6 | High | Trial run and PPAP
PRJ-005 | Rooftop solar 450 kWp (Plant 2) | Sustainability | A. Mehta | V. Rao | Lower grid energy cost | 180 | 176 | 178 | 2025-09-01 | 2026-03-31 | 2026-04-20 | Closed | 100 | 20 | 54 | 22 | Low | Benefit tracking
PRJ-006 | New 450T moulding machine (Plant 1) | Capex | A. Mehta | A. Kulkarni | Capacity for large storage boxes | 310 | 120 | 342 | 2026-06-01 | 2026-12-31 |  | Execution | 40 | 15 | 95 | 0 | Medium | Machine delivery
PRJ-007 | Regrind loop for PP scrap | Productivity | R. Shah | P. Desai | Recover usable PP from runners and rejects | 14 | 13 | 14 | 2025-11-01 | 2026-02-28 | 2026-02-20 | Closed | 100 | 0 | 18 | 15 | Low | Closed

## KPI_Summary
Function KPI summary (optional)
Mandatory | Mandatory | Optional | Optional | Optional | Optional | Optional | Optional | Optional | Optional
KPI_ID | KPI_Name | COIN_KPI_Code | Period | Target | Actual | Unit | Status | Management_Comment | Owner
PRJ-K01 | Projects on schedule | projects.on_schedule | Sep-2026 | 90 | 72 | % | Red | Recover critical path | Projects Head
PRJ-K02 | Budget variance | projects.budget_variance | Sep-2026 | 5 | 8 | % | Amber | Refresh forecast at completion | Projects Head
PRJ-K03 | Benefits realised | projects.benefit_realisation | Sep-2026 | 80 | 35 | % | Red | Validate benefits with Finance | Projects Head

## Actions
Projects, issues and actions (optional)
Mandatory | Optional | Mandatory | Mandatory | Optional | Optional | Mandatory | Mandatory | Mandatory | Optional | Mandatory | Mandatory | Optional | Optional | Optional | Optional | Optional | Optional | Optional | Optional | Optional
Action_ID | Function | Type | Title_or_Issue | Business_Impact | Root_Cause | Priority | Status | Responsible_Person | Support_Functions | Date_Raised | Target_Completion_Date | Actual_Completion_Date | Success_Measure | Baseline | Target | Latest_Result | Escalation_To | Next_Step | Closure_Evidence | Last_Updated
ACT-005 | Projects | Project | Mould 42 cycle-time reduction | Capacity and unit cost | Cooling time above target | High | In progress | V. Rao | Production; Quality | 2026-10-15 | 2026-11-29 |  | Cycle time sec | 38 | 32 | 35 | COO | Run controlled trial |  | 2026-10-20
ACT-006 | Projects | Project | Warehouse barcode rollout | Inventory accuracy | Manual scans not connected to ERP | High | In progress | D. Joshi | IT; Stores; Finance | 2026-10-10 | 2026-12-14 |  | Stock accuracy % | 92% | 99% | 94% | CFO | Complete pilot |  | 2026-10-20

## KPI_Dictionary
KPI definitions (reference — not imported)
COIN_KPI_Code | KPI | Unit | Good direction | Calculation used by CostCubes | Default threshold
projects.on_schedule | Projects on schedule | % | Higher | Approved projects with schedule variance ≤ 0 days ÷ approved projects | 90
projects.budget_variance | Project cost overrun (forecast vs budget) | % | Lower | (Σ forecast at completion − Σ budget) ÷ Σ budget | 5
projects.benefit_realisation | Benefit realisation | % | Higher | Σ benefit realised ÷ Σ benefit target (projects in execution or later) | 60

## _coin (hidden)
FN-PRJ-001
1
COIN-TEMPLATE
454f43e96ea33750
register